

**TERMS OF REFERENCE**

|  |  |
| --- | --- |
| **Consultancy title:** | **Consultancy to develop a functional Complaints and Feedback Mechanism (CFM) system for NPA** |
| **Reporting to:** | Beate Thoresen |
| **NPA offices:** | **Head Office, Oslo, Norway**  **Country and Regional Offices in Norway:**   * South Sudan, plus a selection of other NPA offices TBD |
| **Provisional timeframe:** | 45 working days |
| **Tentative start date:** | 1 November 2024 |

1. **INTRODUCTION**

Norwegian People’s Aid (NPA) is a politically independent membership-based Non-Governmental Organisation working in Norway and in more than 30 countries around the world. Founded in 1939 as the labour movement's humanitarian solidarity organisation, NPA aims to improve people's living conditions and to create a democratic, just and safe society. NPA's international work covers three core areas: Mine Action and Disarmament, Development and Humanitarian responses.

1. **BACKGROUND AND RATIONALE**

NPA works internationally with mine action and disarmament, including demining, conflict preparedness and protection against weapons; humanitarian response, including food security and livelihoods and sexual and gender-based violence and support to civil society. In all interventions, and in line with commitment 5 of the Core Humanitarian Standard on Quality and Accountability (communities and people affected by crisis have access to safe and responsive mechanisms to handle complaints), NPA seeks to gather feedback from the people we serve and the partners we work with. However, this process is not formalised and systematically documented, and hence not always uniformly applied across all locations. This consultancy will draw on existing NPA experiences, policies and tools as well as those developed by other like-minded organisations to develop a new comprehensive and context-specific Complaints and Feedback Mechanism (CFM) system and implementation guidelines. The CFM system will be informed by the Core Humanitarian Standards and the principles of Charter 4 Change, which NPA is signatory to, while being cognisant of the unique context of NPA’s different operational areas.

A small working group including relevant country and Oslo-based staff will serve as an advisory board to the consultant, to ensure adequate anchoring of the project in the organisation. The group’s members will represent different and relevant functions to best build on existing policies and practices. Where necessary, the consultancy will propose updates to existing policies which may be required.

1. **CONSULTANCY OBJECTIVES**

Further to NPA’s newly updated Complaints Policy, the overall objective of this consultancy is to strengthen NPA’s capacity to be accountable to the people we serve and the partners we work with, through development of a functional and context-specific CFM system and implementation guidelines. The specific objectives are:

1. To develop a formalised system and process of soliciting, receiving, processing and responding to the feedback and complaints received from the people we serve and the partners we work with including; multiple example mechanisms designed for our programme types will be the primary output, but NPA will also require other tools to be agreed including moderation guidelines for social media, FAQs, etc. NPA will require the consultant to ensure that mechanisms and tools provided can be integrated within existing and planned operational and MEAL systems.
2. To support NPA in rolling out the CFM policy and mechanism by providing a plan including and by training key NPA staff on the CFM policy, system and the relevant implementation tools. This will include roll out in three countries, Iraq, South Sudan and Mozambique.
3. **CONSULTANCY DELIVERABLES**

The consultancy will develop a procedure which describes how to set up a complaints and feedback mechanism in all the different types of NPA programme. The deliverables for this consultancy therefore include:

1. An assessment of current practices and gaps in NPA’s existing CFM framework following consultation with key stakeholders and policies.
2. To develop a new needs-based and context-specific CFM framework and toolkit that NPA will use in operationalising a CFM system across NPA programmes including:

* NPA head office and country offices;
* NPA mine action operation locations;
* With NPA Cooperating Partners;

1. To provide concrete recommendations to NPA on the structure, staffing and financial requirements needed to ensure that a new CFM functions effectively after the roll-out phase.
2. Toolkit including example mechanisms designed for our programme type, moderation guidelines for social media, FAQs, etc.
3. Tools and guidelines for roll out and a suggested plan.
4. **DURATION OF ASSIGNMENT**

The consultant should complete the assignment within 45 billable days. All the objectives should be achieved fully within this duration.

Suggested schedule:

1. Consultancy identification, October/early November 2024
2. Consultancy onboarding and contract completion by mid-November 2024
3. Working group sign off December 2024
4. SMT sign off before holiday period in January 2025
5. Pilot February 2025
6. Roll out March 2025
7. **SCOPE OF WORK**

The consultancy will look at existing examples of NPA CFM and available evaluations of the same; it will seek information from NPA staff, partner staff and potentially target communities to inform the development of the CFM system – information sources to include NPA consortium experiences, donor requirements, sectoral best practices and partner and self-implementing models. The consultancy will sample at least five different types of NPA partner organisations and target communities from at least five NPA countries. The outcome of the consultancy must take into consideration all types of context and implementation modalities used by NPA (including working with partners and self-implementation) as well as the various relevant accountability standards underpinning this work. The target countries and partners will be identified by NPA.

The consultancy will work with an internal Working Group including communications, HR and representatives from both international departments and attend a total of three meetings to track progress of the project in 2024.

1. **QUALIFICATIONS AND EXPERIENCE**

The independent consultant/consultancy firm must demonstrate experience and expertise as follows:

* Advanced degree in Social Sciences, International Relations, Economics, or other areas of relevance to this consultancy, or equivalent experience.
* More than five years’ experience working on issues of NGO accountability, protection, CHS in developing countries. We are particularly interested in consultants with experience working with organisations that are multi mandated and with a focus on locally led approaches and cooperation with civil society organisations.
* In-depth understanding of AAP, CHS and CFM systems in NGO’s.
* Demonstrated experience in providing high quality Beneficiary Accountability or Protection services for NGO’s.
* Experience conducting remote assignments in similar contexts.
* Fluency in English with excellent writing and presentation skills.
* Ability to manage work and context-related stress while maintaining high performance to achieve the consultancy objectives.

1. **APPLICATION REQUIREMENTS**
2. The technical proposal should include:
   1. Brief explanation about the lead and associate consultants with particular emphasis on previous experience in similar assignments.
   2. Understanding of the terms of reference for this assignment in line with the overall and specific objectives.
   3. Proposed methodology.
   4. Draft work plan.
3. Financial proposal: This should be presented in NOK and should include the consultancy fees only. The number of consultant/s to be engaged in the assignment and their costs should be included in the financial proposal.
4. Examples of previous work conducted that relate to this assignment.
5. Organisational (if it is a company applying) or personal capacity statement (if it is an individual).
6. Resume of the lead consultant and three references from previous clients including full contact details.
7. **EVALUATION CRITERIA**

The applications will be evaluated against the following criteria:

* Sound methodology in undertaking the assignment.
* Relevant technical experience in accountability to affected populations.
* Clear understanding of how to handle sensitive complaints and GBV referral pathways.
* Experience of working with civil society partners or local organisations.
* Experience in conducting similar assignments.
* Experience working in NPA’s programme countries.
* Known and established reliability in delivery of timely and quality services.
* Relevant sector specific technical experience and/or qualifications.

1. **HOW TO APPLY**

Interested applicants should submit applications by email to **tenders@npaid.org** with the subject “CFM CONSULTANCY” on or before **30th October 2024 at 4.00 PM CET time.** Any applications submitted after this date and time will not be considered.